ANNUAL ACTION PLAN

KRISHI VIGYAN KENDRA, SARAIYA (MUZAFFARPUR)

Action Plan April 2018- March 2019

A details target of mandatory activities during 2018-2019

- Training

| Discipline | P/F |  | R/Y |  | E/F |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No | Beneficiaries | No | Beneficiaries | No | Beneficiaries | No | Beneficiaries |
| Plant protection | 18 | 390 | 4 | 70 | 4 | 80 | 24 | 490 |
| Soil Science | 14 | 350 | 4 | 105 | 4 | 90 | 22 | 515 |
| Horticulture | 12 | 286 | 6 | 141 | 4 | 80 | 22 | 478 |
| Home Science | 12 | 300 | 9 | 210 | 8 | 220 | 29 | 680 |
| Total | 56 | 1346 | 23 | 526 | 20 | 470 | 97 | 2163 |

- OFT/FLD/Soil testing/Seed production

| Discipline | OFT |  | FLD |  | Extension activities |  | Seed production/planting material |  | Soil testing |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No | No. of Beneficiaries | No | No. of Farmers | No | No. of Farmers | Area in ha/No | Seed in q/No | No | No. of Farmers |
| Plant protection | 2 | 28 | 3 | 85 | 863 | 2205 | 14.4 | 286 |  |  |
| Soil Science | 2 | 10 | 2 | 100 | 668 | 2217 |  |  | 500 | 500 |
| Horticulture | 2 | 20 | 3 | 40 | 662 | 1967 | 6 (planting/seedlings material) | 100000 |  |  |
| Home Science | 2 | 13 | 3 | 50 | 311 | 1617 |  |  |  |  |
| Total | 8 | 71 | 11 | 275 | 2504 | 8006 |  |  | 500 | 500 |

- CFLD/CSISA Project

| Discipline | CSISA(OFT) |  |  |  | CFLD |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Kharif (Paddy) |  | Rabi(wheat |  |  |  |
|  | No | No. of Farmers | No | No. of Farmers | No | No. of Farmers |
| Plant protection | 12 | 120 | 10 | 100 |  |  |
| Soil Science |  |  |  |  | 4 | 200 |
| Total | 12 | 120 | 10 | 100 | 4 | 200 |

- Training

- Farmers and Farm women

- Soil Science

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST | Others |  | Total |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  | M | F | M | F |  | T |
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soil testing | Soil Sampling method and fertilizer recommendation for farmers doubling income | Off | 1 | 1 | 3 | 2 | 0 | 15 | 05 | 18 | 7 |  | 25 |
| INM | Green mannuring through Sesbania rostrata & Vigna rediata | Off | 1 | 1 | 5 | 0 | 0 | 20 | 03 | 25 | 03 |  | 28 |
| Vermi-composting | Vermi-compost production for organic farming | On/Off | 1 | 1 | 5 | 0 | 0 | 20 | 03 | 25 | 03 |  | 28 |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INM | Importance of vermi-compost & bio-fertilizer in Kharif crops | Off | 1 | 1 | 5 | 0 | 0 | 20 | 03 | 25 | 03 |  | 28 |
| INM | Brown mannuring through Sesbania rostrata in rice | Off | 1 | 1 | 5 | 0 | 0 | 20 | 01 | 25 | 01 |  | 26 |
| Vermin-composting | Vermicompost production and its uses | Off | 1 | 1 | 5 | 0 | 0 | 20 | 01 | 25 | 01 |  | 26 |
| Organic farming | Use of different organic manure in cereal and vegetable crops | Off | 1 | 1 | 5 | 0 | 0 | 20 | 02 | 25 | 02 |  | 27 |
| Oct to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production and use of organic inputs | Vermicompost production and its uses | On | 1 | 1 | 5 | 0 | 0 | 20 | 02 | 25 | 02 |  | 27 |
| Soil testing | Soil testing methods and fertilizer recommendation | Off | 1 | 1 | 5 | 0 | 0 | 20 | 02 | 25 | 02 |  | 27 |
| Micronutrient deficiency in crops | Diagnosis of micronutrient deficiency and its reclamation | Off | 1 | 1 | 5 | 0 | 0 | 20 | 01 | 25 | 01 |  | 26 |
| Soil and water conservation | Moisture conservation through different practices of mulching in crop | Off | 1 | 1 | 5 | 0 | 0 | 20 | 02 | 25 | 02 |  | 27 |
| Jan to March |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resource conservation technology | Cultivation of wheat through zero tillage and fertilizer management | Off | 1 | 1 | 5 | 0 | 0 | 20 | 0 | 25 |  | 0 | 25 |
| INM | INM in green gram through Rhizobium culture and PSB | Off | 1 | 1 | 5 | 0 | 0 | 20 | 0 | 25 |  | 0 | 25 |
| Soil fertility management | Soil fertility management through vermicompost | Off | 1 | 1 | 5 | 0 | 0 | 20 | 0 | 25 |  | 0 | 25 |
| Total |  |  | 14 | 14 | 68 | 2 | 0 | 275 | 25 | 343 |  | 27 | 370 |

- Plant protection

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  |  | ST | Others |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  |  | M | F | M | F | T |
| 1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 | 11 | 12 |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mushroom Cultivation | Milky mushroom cultivation. | On | 3 | 1 | 03 | 0 |  | 0 | 17 | 02 | 20 | 02 | 22 |
| IPM | IPM in Summer vegetable. | On | 3 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| Bio control of pest and disease | Bio control of pest and disease in litchi crop | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| IPM | IPM in Cow pea | Off | 1 | 1 | 03 | 0 |  | 0 | 17 | 02 | 20 | 02 | 22 |
| IDM | Seed and seedling treatment in paddy | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IDM | Important seed and soil borne disease of Paddy and its management | On | 3 | 1 | 02 | 0 |  | 0 | 20 | 03 | 22 | 03 | 25 |
| IPM | IPM in Paddy crop | Off | 1 | 1 | 02 | 0 |  | 0 | 20 | 03 | 22 | 03 | 25 |
| IPM | IPM in Maize crop | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| IPM | IPM in Paddy crop | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| Oct to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IDM | Important disease of Pulse and Oilseed and their management | On | 3 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 20 |
| IDM | Important disease of potato and tomato and their management | On | 3 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| IPM | IPM in oilseed and pulses | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 02 | 20 | 02 | 22 |
| IDM | IDM in cabbage and cauliflower | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 0 | 20 | 0 | 20 |
| IPM | IPM in potato and tomato | Off | 1 | 1 | 02 | 0 |  | 0 | 18 | 0 | 20 | 0 | 20 |
| Jan to March |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPM | IPM in Mango and litchi | On | 03 | 1 | 02 |  | 0 | 0 | 18 | 0 | 20 | 0 | 20 |
| IDM | IDM in Mango and litchi | Off | 1 | 1 | 02 |  | 0 | 0 | 18 | 0 | 20 | 0 | 20 |
| IPM | IPM in Green gram | Off | 1 | 1 | 02 |  | 0 | 0 | 18 | 0 | 20 | 0 | 20 |
| IPM | IPM in summer vegetable | Off | 1 | 1 | 02 |  | 0 | 0 | 18 | 0 | 20 | 0 | 20 |
| Total |  |  | 30 | 18 | 38 |  | 0 | 0 | 326 | 26 | 364 | 26 | 390 |

- Home science

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST | Others |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  | M | F | M | F | T |
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |
| Minimization of nutrient loss in processing | Introducing water soluble nutrients and ways to minimizing it losses | On | 1 | 1 | 0 | 5 | 0 | 5 | 15 | 5 | 20 | 25 |
| Designing and development for high nutrient efficiency diet | Developing Iron rich diet by using dried green leafy vegetable | On | 1 | 1 | 0 | 4 | 0 | 2 | 14 | 2 | 18 | 20 |
| Designing and development for high nutrient efficiency diet | Developing Vitamin “A” rich diet for preschool children by using Vit.”A” rich food | Off | 1 | 1 | 0 | 5 | 0 | 0 | 20 | 0 | 25 | 25 |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |
| Designing and development of low cost diet. | Cheap and locally available nutrient rich source of food | On | 1 | 1 | 0 | 5 | 0 | 5 | 15 | 5 | 20 | 25 |
| Women and child care | Importance of Weaning and supplementary foods and methods of preparing them | Off | 01 | 1 | 0 | 5 | 0 | 0 | 20 | 0 | 25 | 25 |
| Designing and development for high nutrient efficiency diet | Fiber rich and low energy diet for obese and diabetic people | Off | 1 | 1 | 0 | 5 | 0 | 10 | 10 | 10 | 15 | 25 |
| Oct to Dec |  |  |  |  |  |  |  |  |  |  |  |  |
| Value addition | Scientific method of drying vegetables | Off | 2 | 1 | 0 | 10 | 0 | 0 | 20 | 0 | 30 | 30 |
| Drudgery reduction | Farm mechanization | Off | 1 | 1 | 0 | 5 | 0 | 0 | 20 | 0 | 25 | 25 |
| Value addition | Importance of Aonla and method of preparing preserved items from it. | On | 2 | 1 | 0 | 5 | 0 | 0 | 20 | 0 | 25 | 25 |
| Jan to March |  |  |  |  |  |  |  |  |  |  |  |  |
| Mushroom production | Mushroom cultivation | On | 1 | 1 | 0 | 10 | 0 | 0 | 20 | 0 | 30 | 30 |
| Value addition | Importance of Aonla and method of preparing preserved items from it. | Off | 2 | 1 | 0 | 5 | 0 | 0 | 15 | 0 | 20 | 20 |
| Designing and development for high nutrient efficiency diet | Green leafy vegetables as a source of iron and method of its use | Off | 1 | 1 | 0 | 5 | 0 | 0 | 20 | 0 | 25 | 25 |
| Total |  |  | 15 | 12 | 0 | 69 | 0 | 22 | 209 | 22 | 278 | 300 |

- Horticulture

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST | Others |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  | M | F | M | F | T |
| 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |
| Protective cultivation | Protective cultivation of tomato and cucumber | On | 3 | 1 | 5 | 0 | 0 | 25 | 3 | 30 | 3 | 30 |
| ICM | Scientific cultivation of ginger | Off | 1 | 1 | 5 | 2 | 0 | 15 | 3 | 20 | 5 | 25 |
| INM | Care and management of litchi orchard | Off/On | 1 | 1 | 5 | 2 | 0 | 10 | 3 | 15 | 5 | 20 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |
| Nursery raising | Nursery raising of fruit crops. like Mango Guava and Litchi | On | 3 | 1 | 3 | 2 | 0 | 12 | 3 | 15 | 5 | 20 |
| Orchard management | Care and management of mango orchard. | Off | 1 | 1 | 5 | 0 | 0 | 20 | 3 | 25 | 3 | 25 |
| ICM | Package and practices of guava production | Off/On | 1 | 1 | 3 | 2 | 0 | 15 | 3 | 18 | 5 | 23 |
| Oct. to Dec. |  |  |  |  |  |  |  |  |  |  |  |  |
| Nursery raising | Nursery raising of different seasonal veg. | On | 3 | 1 | 5 | 2 | 0 | 20 | 3 | 25 | 5 | 30 |
| ICM | Cultivation of early cauliflower | Off | 1 | 1 | 3 | 2 | 0 | 12 | 3 | 15 | 5 | 20 |
| ICM | Scientific cultivation of marigold | Off/On | 1 | 1 | 3 | 2 | 0 | 15 | 3 | 18 | 5 | 20 |
| Jan to March |  |  |  |  |  |  |  |  |  |  |  |  |
| Nursery raising | Technique of nursery raising for summer vegetables | Off | 2 | 1 | 2 | 1 | 0 | 13 | 4 | 15 | 5 | 20 |
| Yield increment | Scientific cultivation of Okra | On | 1 | 1 | 5 | 2 | 0 | 12 | 3 | 17 | 5 | 22 |
| ICM | Scientific cultivation of Summer vegetable | On/Off | 1 | 1 | 5 | 2 | 0 | 12 | 3 | 17 | 5 | 22 |
| Total |  |  | 19 | 12 | 49 | 19 | 0 | 181 | 37 | 230 | 56 | 286 |

- Rural Youth

- Soil Science

| Thematic Area | Title | Venue |  | Duration | No. of courses | SC |  | ST | Others |  |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | M | F |  | M |  | F |  | M | F | T |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Soil testing | Method of sampling, Soil analysis and its recommendation for soil health | On |  | 05 | 01 | 5 | 0 | 0 |  | 15 |  | 05 | 20 | 5 | 25 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vermi compost | Vermi-compost and vermiwash production technique | On |  | 03 | 1 | 5 | 0 | 0 |  | 20 |  | 05 | 25 | 5 | 30 |
| Oct. to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soil testing | Soil sampling technique and analysis |  | On | 05 | 1 | 5 | 0 | 0 |  | 15 |  | 03 | 20 | 03 | 30 |
| Dec. to March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production of organic input | Vermicompost production and its utility |  | On | 03 | 1 | 5 | 0 | 0 |  | 20 |  | 02 | 25 | 02 | 30 |
| Total |  |  |  | 16 | 4 | 20 | 5 | 0 |  | 70 |  | 15 | 90 | 15 | 105 |

- Plant Protection

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST |  | Others |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  |  | M | F | M | F | T |
| Apr. to June |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production of organic input | Production technique of Trichoderma viride | On | 5 | 1 | 5 | 0 | 0 | 10 |  | 05 | 15 | 05 | 20 |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Seed production | Mushroom spawn production | On | 5 | 1 | 2 | 1 | 0 | 10 |  | 2 | 12 | 03 | 15 |
| Oct to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Seed production | Mushroom cultivation | On | 5 | 1 | 02 | 0 | 0 | 13 |  | 05 | 15 | 05 | 20 |
| Jan-March |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Seed production | Mushroom spawn production | On | 5 | 1 | 2 | 1 | 0 | 10 |  | 2 | 12 | 3 | 15 |
| Total |  |  | 20 | 4 | 11 | 02 | 0 | 43 |  | 14 | 54 | 16 | 70 |

- Home Science

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST |  | Others |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  |  | M |  | F | M | F | T |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Value addition | Method of preparing squash, jelly, sauce, toffee from locally available fruits and vegetables | On | 05 | 01 | 0 | 05 | 0 | 5 |  | 20 |  | 5 | 25 | 30 |
| Value addition | Method of preparing preserved item from mango and other fruits | On | 05 | 01 | 0 | 05 | 0 | 5 |  | 20 |  | 5 | 25 | 30 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Value addition | Method of preparing poshak bari by adding green leafy vegetables | On | 04 | 01 | 0 | 03 | 0 | 5 |  | 12 |  | 5 | 15 | 20 |
| Tailoring and stitching | Stitching of soft toys | On | 03 | 01 | 0 | 05 | 0 | 5 |  | 15 |  | 5 | 20 | 25 |
| Oct. to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enterprise development | Method of making lac bangle | On | 06 | 01 | 0 | 05 | 0 | 5 |  | 10 |  | 5 | 15 | 20 |
| Mushroom production | Oyster mushroom cultivation | On | 03 | 01 | 0 | 5 | 0 | 5 |  | 15 |  | 5 | 20 | 25 |
| Mushroom production | Button mushroom cultivation | On | 03 | 01 | 0 | 5 | 0 | 0 |  | 15 |  | 0 | 20 | 20 |
| Jan. to March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tailoring and stitching | Stitching of soft toys | On | 03 | 01 | 0 | 5 | 0 | 0 |  | 15 |  | 0 | 20 | 20 |
| Tailoring and stitching | Stitching of ladies purse | On | 05 | 01 | 0 | 05 | 0 | 0 |  | 15 |  | 0 | 20 | 20 |
| Total |  |  | 37 | 9 | 0 | 43 | 0 | 0 |  | 137 |  | 30 | 180 | 210 |

- Horticulture

| Thematic Area | Title | Venue |  | Duration | No. of courses | SC |  |  | ST |  | Others |  | Total |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | M |  | F |  |  | M | F | M | F |  | T |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Protected cultivation | Use and importance of Poly house, Greenhouse, Glass house etc. for vegetable cultivation | On |  | 4 | 1 | 5 | 0 |  | 0 | 12 |  | 3 | 20 | 3 | 23 |  |
| ### Seed production | Seed production technique of lobia | On |  | 4 | 1 | 5 | 0 |  | 0 | 13 |  | 2 | 20 | 2 | 22 |  |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Seed production | Seed production of early cauliflower |  | On | 3 | 1 | 5 |  | 0 | 0 | 13 |  | 2 | 20 | 2 | 22 |  |
| ### Commercial fruit production | Scientific cultivation of Banana and Guava |  | On | 4 | 1 | 4 |  | 0 | 0 | 18 |  | 2 | 24 | 2 | 26 |  |
| Oct. to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Integrated farming | Integrated farming system through developing Agri-Horti- Fishery system |  | On | 4 | 1 | 6 |  |  | 0 | 17 |  | 2 | 25 | 2 | 27 |  |
| Jan to March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Low volume high value crop | Protective cultivation of vegetable like Cucumber and Capsicum |  | On | 3 | 1 | 5 |  |  | 0 | 14 |  | 1 | 20 | 1 | 21 |  |
| Total |  |  |  | 22 | 6 | 30 |  | 0 | 0 | 87 |  | 12 | 129 | 12 | 141 |  |

- Extension functionaries training

- Soil Science

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  |  | ST | Others |  | Total |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  |  | M | F | M |  |  | F | T |  |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INM | Scope and importance of Green and brown Mannuring | On | 02 | 01 | 05 |  | 0 | 0 | 15 | 05 | 20 |  | 05 |  |  | 25 |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vermi-composting | Process of vermi-composting technique and its uses. | On | 02 | 01 | 05 |  | 0 | 0 | 10 | 05 |  | 15 | 05 |  |  | 20 |
| Oct to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INM | Importance of Macro and micro nutrients in crop production. | On | 02 | 01 | 05 |  | 0 | 0 | 15 | 05 |  | 20 | 05 |  |  | 25 |
| Jan. to Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Soil testing | Soil testing: A tools for farmers doubling income | On | 02 | 01 | 05 |  | 0 | 0 | 10 | 05 |  | 15 | 05 |  |  | 20 |
| Total |  |  | 08 | 04 | 20 |  | 0 | 0 | 50 | 20 |  | 70 | 20 |  |  | 90 |

- Plant protection

| Thematic Area | Title | Venue | Duration | No. of courses | SC |  | ST |  | Others |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  |  | M |  | F | M | F | T |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### IPM | IPM in Green gram | On | 02 | 1 | 5 | 0 | 0 |  |  | 10 | 05 | 15 | 05 | 20 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPM | IPM in pigeon pea | On | 02 | 1 | 5 | 0 | 0 |  | 10 |  | 05 | 15 | 05 | 20 |
| Oct. to Dec |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPM | IPM in wheat crop | On | 02 | 1 | 5 | 0 | 0 | 10 |  |  | 05 | 15 | 05 | 20 |
| Jan. to March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IPM | IPM in Mango and Litchi | On | 02 | 1 | 5 | 0 | 0 | 10 |  |  | 05 | 15 | 05 | 20 |
| Total |  |  | 8 | 4 | 20 | 0 | 0 | 40 |  |  | 20 | 60 | 20 | 80 |

- Home Science

| Thematic Area | Title | Venue | Duration | No. of courses | SC | ST |  | Others |  |  | Total |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | M | F |  | M | F |  | M | F |  |  | T |  |
| April to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Household food security | Balance diet for different age group | Off | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| Low cost and nutrient efficient diet designing | Cheap and locally available nutrient rich food | On/Off | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| July to Sep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Women and child care | Preparation of low cost weaning food for baby | On/Off | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| Women and child care | Importance of diet during pregnancy | On | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| Oct to Dec. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Women and child care | Importance of diet during lactation | Off | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| Women and child care | Importance of supplementary and weaning food and method of its preparation | Off | 01 | 01 | 0 | 05 | 0 | 2 |  | 20 | 2 |  | 25 | 27 |  |
| Jan. to Mar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Women and child care | Method of preparing high protein and caloric rich dishes for preschool children | On | 01 | 01 | 0 | 05 | 0 | 03 |  | 20 | 03 |  | 25 | 28 |  |
| Low cost and nutrient efficient diet designing | Use of dried green leafy vegetable in diet | On | 01 | 01 | 0 | 05 | 0 | 05 |  | 20 | 05 |  | 25 | 30 |  |
| Total |  |  | 08 | 08 | 0 | 40 | 0 | 20 |  | 160 | 20 |  | 200 | 220 |  |

- Horticulture

| Thematic Area | Title | Venue |  | Duration |  | No. of courses |  | SC |  | ST |  |  | Others |  |  | Total |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | M |  | F |  |  | M |  | F | M |  | F | T |
| Apr. to June |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Protective cultivation | Protective cultivation of commercial flower like tuberose and rose for income generation. | On/Off | 2 |  | 1 |  | 5 |  | 0 |  | 0 | 10 |  | 5 |  | 15 | 5 |  | 20 |
| July to Sept |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Entrepreneurship development | Graft and air layering preparation of Mango and litchi with the help of SHGs group. | Off/On | 2 |  | 1 |  | 5 |  | 0 |  | 0 | 10 |  | 5 |  | 15 |  | 5 | 20 |
| Oct. to Dec. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ### Production and use of organic input | Scope and importance of organic farming of vegetable crop production. | Off | 2 |  | 1 |  | 5 |  | 0 |  | 0 | 10 |  | 5 |  | 15 |  | 5 | 20 |
| Jan. to March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Rejuvenation of old orchard | Scope and importance of rejuvenation in litchi and mango | On | 2 |  | 1 |  | 5 |  | 0 |  | 0 | 10 |  | 5 |  | 15 |  | 5 | 20 |
| Total |  |  | 8 |  | 4 |  | 20 |  | 0 |  | 0 | 40 |  | 20 |  | 60 |  | 20 | 80 |

- Front Line Demonstration :

| Sl. No. |  | Crop | Variety |  | Season | Area (ha)/No | Quantity | No. of demonstration |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Crop production/ Soil Science |  |  |  |  |  |  |  |  |  |  |
| 1. |  | Rice | Nilam |  | Kharif 2018 | 20.0 | 8.0 q | 50 |  |  |
| 2. |  | Wheat | HD 2967/K307 |  | Rabi 2018 | 20.0 | 20.0q | 50 |  |  |
| Plant protection |  |  |  |  |  |  |  |  |  |  |
| 1 |  | Cabbage and cauliflower | Trichoderma viride |  | Rabi | 10.0 | 50kg |  | 50 |  |
| 2 |  | Mushroom | Oyster/Milkey |  | Rabi | 10 unit | 100kg |  | 10 |  |
| 3 |  | Litchi | Neem oil 300 ppm |  | Kharif | 10.0 | 25 Lt |  | 50 |  |
| Horticulture |  |  |  |  |  |  |  |  |  |  |
| 1. |  | Potato | K. Pokhraj /K.Sindoori |  | Rabi 2018 | 1.0 | 20q |  | 10 |  |
| 2. |  | Marigold seed ling | African marigold |  | Rabi 2018 | 2.0 | 500g |  | 10 |  |
| 3. |  | Cow pea | Kashi Kanchan |  | Summer2019 | 5.0 | 50kg |  | 20 |  |
| Home Science |  |  |  |  |  |  |  |  |  |  |
| 1. | Mushroom |  |  | Oyster | Rabi | - | 20kg |  |  | 20 |
| 2. | Mushroom |  |  | Milky | Kharif | - | 20kg |  |  | 20 |
| 3. | Green gram |  |  | Advance Storage bag | Rabi/Kharif | - | 50 |  |  | 10 |

- Cluster Front Line Demonstration

| Sl. No. | Crop | Variety | Season | Area (ha) | Quantity (q) | No. of demonstration |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Red gram | Below 10 year as per availability | Kharif | 20 | 4.00 | 50 |
| 2 | Soybean | Below 10 year as per availability | Kharif | 10 | 6.00 | 25 |
| 3 | Sesamum | Below 10 year as per availability | Kharif | 20 | 1.00 | 50 |
| 4 | Rapeseed & mustard | Below 10 year as per availability | Rabi | 40 | 2.00 | 100 |
| 5 | Lentil | as per availability | Rabi | 20 | 8.00 | 50 |
| 6 | Green gram | Below 10year as per availability | Summer | 30 | 12.00 | 75 |

- On Farm Trial (OFT)

- Soil Science

OFT-1

| Title |  | : | Effect of Fe on different stages of paddy under aerobic condition |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Problem identified |  | : | Low yield due iron deficiency in aerobic condition |  |  |  |  |
| Source of technology |  | : | Dr.R.P.C.A.U, Pusa,Samastipur. |  |  |  |  |
| Performance Indicator |  | : | Soil test, Yield, yield attributes and economics. |  |  |  |  |
| Thematic area |  | : | INM |  |  |  |  |
| Design |  | : | RBD |  |  |  |  |
| Area |  | : 1.0 ha |  |  |  |  |  |
| Technology option |  | Treatments |  |  |  |  | No. of farmers |
| Farmer’s practice |  | RDF |  |  |  |  | 5 |
| T.O: 1 |  | Fe SO4 @1 % at 15 DAS |  |  |  |  |  |
| T.O: 2 |  | Fe SO4 @1 % at 15 DAS and 35 DAS |  |  |  |  |  |
| T.O: 3 |  | Fe SO4 @1 % at 15 DAS, 35 DAS and 55 DAS |  |  |  |  |  |

OFT-2

| Title | : | Effect of plant density for production of Rabi maize. |  |  |
| --- | --- | --- | --- | --- |
| Problem | : | Low yield due to improper fertilizer management and spacing |  |  |
| Source | : | Dr.R.P.C.A.U, Pusa, Samastipur. |  |  |
| Indicator | : | Soil test ,Yield, yield attributes and economics |  |  |
| Thematic area | ; | INM |  |  |
| Design | : | RBD |  |  |
| Area | : | 1.0ha |  |  |
| Technology option |  | Treatments | No. of farmers |
| Farmer’s Practice : |  | Improper fertilizer management and spacing(Spacing for sowing 60 X 20 cm and 120: 60: 50 Kg/ ha NPK) | 5 |
| T.O-1 |  | Spacing for sowing 40X 20 cm and 150: 75: 50 Kg/ ha NPK |  |
| T.O 2 |  | Spacing for sowing 40X 20 cm and 125: 75: 50 Kg/ ha NPK |  |
| T.O 3 |  | Spacing for sowing 40X 20 cm and 100: 75: 50 Kg/ ha NPK |  |

- Plant protection

OFT – 1

| Title |  | : | Effect of chemicals for control of Mungbean yellow mosaic virus (MYMV) in Mungbean (Vigna radiata L.). |  |  |
| --- | --- | --- | --- | --- | --- |
| Problem identified |  | : | Infestation caused by whitefly. |  |  |
| Source of technology |  | : | GKVK Bengluru,Karnataka,India |  |  |
| Performance Indicator |  | : | Yield, % damage,yield attributes & economics. |  |  |
| Thematic area |  | : | IPM |  |  |
| Design |  | : | RBD |  |  |
| Area |  | : | 2 ha. |  |  |
| Technology option | Treatments |  |  | No. of farmers |
| T 1 | One spray of imidachlorprid 17.8%SL @ 0.5 ml/lt. of water. |  |  | 6 |
| T2 | Seed treatment with imidachlorprid 17.8%SL @ 0.5 ml/lt. of water. |  |  |  |
| T3 | T1 + 2 spray of imidachlorprid 17.8%SL @ 0.5 ml/lt. of water. |  |  |  |
| T4 | T1 + 2 spray of Triazophos 40% EC @1.5 ml/lt.of water. |  |  |  |
| T5 | T1 + 2 spray of neem oil 300PPM @ 3 ml/Lt |  |  |  |

OFT: 2

| Title |  | : | Management of Panama wilt in Muzaffarpur district. |  |
| --- | --- | --- | --- | --- |
| Problem identified |  | : | Crop loss due to wilt disease. |  |
| Source of technology |  | : | Department of plant pathology, Dr. R. P. C. A. U, Pusa, Samastipur. |  |
| Performance indicator |  | : | Pathogen identification, Disease incidence (%), No. of plant affected, Yield and yield attributes. |  |
| Thematic area |  | : | IDM |  |
| Design |  | : | RBD |  |
| Area |  | : | 0.2 ha X 30 |  |
| Technology option |  | Treatments |  |  | No. of farmers |
| Farmer’s Practice |  | Used Phorate and Chloriopyriphos. |  |  | 05 |
| T.O-1 |  | Through integrated approach (dipping the disease free paired sucker in Carbendazim solution (0.2%) for 30 minutes+ 250 g organic manure/ neem cake at the time of planting + drenching with 0.2 % Carbendazim @ 2 to 3 Lt/Plant at 2nd, 4th and 6th month after planting + stem injection with Carbendazim @ 3 ml of 2% solution at 3rd, 5th and 7th month after planting.) |  |  |  |
| T.O- 2 |  | Management through non-chemical ( disease free sucker+ vermicompost @ 250 g/pit + soil application of Trichoderma viride (107) @ 10 g + Psedumonas fluoroscens @ 50g /sucker at 0,2nd and 4th month after planting found highly effective with more than 55 % wilt reduction. |  |  |  |

- Horticulture

OFT: 1

| Title | : | Integrated Nutrient Management in Potato |
| --- | --- | --- |
| Problem diagnosed | : | Low yield of potato due to indiscriminate use of chemical fertilizer |
| Source of technology | : | Dr.R.P.C.A.U, Pusa, Samastipur |
| Production system and thematic area | : | INM |
| Design | : | RBD |
| Performance indicator | : | Yield, Net return and B:C ratio |

Details of technology

| Technology option | Treatments | No. of farmers |
| --- | --- | --- |
| Farmer’s practice | N:P:K(125:75: 75) | 10 |
| T.O 1- | 90 % recommended dose of chemical fertilizer + 10 % vermicompost. |  |
| T.O 2- | 80% recommended dose of chemical fertilizer + 20 % vermicompost. |  |

- Recommended dose:N:P:K (150:90:100)

OFT-2

| Title | : | Effect of sulphur for improving bulb yield and its storage durability of onion. |
| --- | --- | --- |
| Problem diagnoses | : | Inferior bulb yield and low storage life. |
| Source of technology | : | Dr.R.P.C.A.U, Pusa, Samastipur |
| Production system and thematic area | : | Bulb quality management and INM |
| Design | : | RBD |
| Indicator | : | Yield, Net return, storability and ,B:C ratio |

Details of technology

| Technology option | Treatments | No. of farmers |
| --- | --- | --- |
| Farmer’s practice | No use of sulphur | 10 |
| T.O 1 | Soil application of 20 kg /ha sulphur |  |
| T.O 2 | Soil application of 30 kg /ha sulphur |  |
| T.O 3 | Soil application of 40 kg /ha sulphur |  |

- Home science

OFT-1

| Title | : | Assessment of weight and spoilage loss of onion by using different methods of storage. |
| --- | --- | --- |
| Problem diagnosed | : | Onion is a cash crop but due to improper storage facility it begin to deteriorate after harvest and farmers get poor price of their product |
| Source of technology | : | KVK, Hooghly and NHRDF |
| Production system and thematic area | : | Post harvest technology |
| Design | : | RBD |
| Indicator | : | Physiological wt. loss, percentage spoilage loss, total loss percent and B:C ratio |

| Technology option | Treatments | No. of farmers |
| --- | --- | --- |
| Farmer’s practice | Storage in room on uncemented floor | 5 |
| T.O 1- | Storage on gunny mat kept at uncemented floor |  |
| T.O 2.- | Storage at bamboo rack (Chali) |  |
| T.O.3- | Storage in improved low cost onion storage structure developed by NHRDF |  |

Note; The Improved low cost onion storage structure developed by NHRDF cost nearly 7000 having capacity to store 1300 kg onion (size 5’*4’*5’). In one cubic feet structure 20 kg onion can be stored.

OFT-2

| Title | : | Storage of leafy vegetables and other green vegetables in zero energy cool chamber to retain the freshness of vegetables to get maximum return. |
| --- | --- | --- |
| Problem diagnosed | : | Green leafy vegetables deteriorate rapidly after harvesting and farmers get poor price of their products. The physiological weight loss of even more than 5% of most of the vegetable are not fit for consumption |
| Source of technology | : | College of engineering, DrRPCAU, pusa, samastipur. |
| Production system and thematic area | : | Post harvest technology |
| Design | : | RBD |
| Indicator | : | Percentage physiological wt. loss , percentage spoilage loss, BC ratio. |

| Technology option | Treatments | No. of farmers |
| --- | --- | --- |
| Farmer’s practice | Storage at floor. | 3 |
| T.O 1 | Storage in bamboo basket |  |
| T.O 2 | Storage at aerated gunny bag |  |
| T.O 3 | Storage in zero energy cool chamber. |  |

- Extension activity

| Nature of Extension Activity | Horticulture | Soil science | Plant protection | Home science | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | No | participants |
| Field Day | 3 | 7 | 4 | 3 | 16 | 600 |
| Scientific visit to farmers field | 100 | 100 | 100 | 50 | 350 | 350 |
| Farmers visit at KVK | 00 | 000 | 00 | 00 | 1000 | 1000 |
| Exposure Visit | 1 | 1 | 1 | 1 | 4 | 200 |
| Kisan Ghosthi | 2 | 2 | 2 | 2 | 8 | 400 |
| TV talks | 2 | 2 | 2 | 2 | 8 | - |
| Popular articles/Booklet | 2 | 2 | 2 | 2 | 8 | 8000 |
| Advisory Services | 500 | 500 | 500 | 250 | 1750 | 1750 |
| Soil health camp |  | 4 |  |  | 4 | 200 |
| Ex-trainees sammelan | 1 | 1 | 1 | 1 | 4 | 120 |
| Self help group convener meet |  |  |  | 1 | 1 | 25 |
| Celebration of important day | 00 | 00 | 00 | 00 | 6 | 300 |
| PACKS member convener meet | 1 |  |  |  | 1 | 25 |
| Pesticide dealers meet |  |  | 1 |  | 1 | 25 |
| Fertilizer dealers meet |  | 1 |  |  | 1 | 25 |
| Success story | 1 | 1 | 1 | 1 | 4 | - |
| Mobile services | 50 | 50 | 250 | 50 | 400 | 400 |
| Total | 663 | 671 | 864 | 363 | 3566 | 13420 |

- Seed and planting material production:

| Seed |  |  | Planting material |  |  |
| --- | --- | --- | --- | --- | --- |
| Crop | Area(ha) | Production (q) | Crop | Area (ha) | No. |
| Paddy | 2.0 | 50.00 | Brinjal | 0.05 | 20000 |
| Red gram/ Soyabean | 2.0 | 20.00 | Tomato | 0.05 | 20000 |
| Wheat | 5.0 | 100.00 | Chilli | 0.05 | 20000 |
| Green gram | 2.0 | 12.00 | Capsicum | 0.05 | 10000 |
| Mustard | 3.0 | 30.00 | Cabbage | 0.05 | 10000 |
| Potato | 0.4 | 80.00 | Cauliflower | 0.05 | 20000 |
| Total | 14.4 | 296.00 | Total | 0.05 | 100000 |

6.  Fund requirement during the financial year 2018-19

| S. No. | Particulars | Fund requirement |
| --- | --- | --- |
| A. Recurring Contingencies |  |  |
| 1 | Pay & Allowances | 8854464.00 |
| 2 | Traveling allowances | 200000.00 |
| 3 | HRD | 100000.00 |
| 4 | Contingencies |  |
| A | Stationery, telephone, postage and other expenditure on office running, publication of Newsletter and library maintenance (Purchase of News Paper & Magazines) | 850000.00 |
| B | POL, repair of vehicles, tractor and equipments Electricity bill |  |
| C | Meals/refreshment for trainees Participated in Farmers and Farm women training (ceiling up to Rs.50/day/trainee be maintained) | 250000.00 |
|  | Meals/refreshment for trainees Participated in Rural youth training (ceiling up to Rs.50/day/trainee *60 be maintained) | 150000.00 |
|  | Meals/refreshment for trainees Participated in Extension functionaries (ceiling up to Rs.75/day/trainee *60 be maintained) | 70000.00 |
| D | Training material (posters, charts, demonstration material including chemicals etc. required for conducting the training) | 100000.00 |
| E | Frontline demonstration except oilseeds and pulses (minimum of 30 demonstration in a year) | 150000.00 |
| F | On farm testing (on need based, location specific and newly generated information in the major production systems of the area) | 75000.00 |
| Misc Soil testing chemical |  | 50000.00 |
| Total |  |  |
| TOTAL (A) |  |  |
| B. Works |  |  |
| 1 | Equipment and chemical for lab(Soil Science, Home Science and Plant protection | 200000 |
| 2 | Farm equipments( Zero till seed drill cum fertilizer machine, Reepar cum binder, Weighing machine, etc) | 200000 |
| 3 | Half shaded threshing flo0r Shade 1200 sq ft | 1000000 |
| 4 | Shade for MSTL VAN | 200000 |
| 5 | Pathology lab equipments | 50000 |
| 6 | Solar tree | 500000 |
| 7 | Repairing and maintenance of Soil Testing lab | 200000 |
| 8 | IT equipment (LCD/ CAMERA/PROJECTOR etc | 100000 |
| TOTAL (B) |  |  |
| TOTAL (A+B) |  |  |